## Cases
CASEID | CUSTOMER | DATETIME | SUBJECT | SEVERITY | TYPE | STATUS | REASON | PRODUCT | FOUND BY | LASTCHANGE | SITE | TOTAL HOURS | ACTYPE
403516 | Claro AR PY UY (O&M) | 2022-08-31 16:49 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 1/9/2022 - ON | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-09-01 01:03 | Claro AUP - URUGUAY | 1 | Tariff Activities
403509 | Claro AR PY UY (O&M) | 2022-08-31 11:13 | CTITUY 077_2022 -WO0000003888467- CCC_8245- (Triplica 7; 8; 9 Y 12 de septiembre Tn3 UY) [SEVERITY 1 | Minor | Tariff Request | Under investigation |  | Prepaid IN | Fabian Pizzatti | 2022-09-02 16:08 | Claro AUP - URUGUAY
403499 | Claro AR PY UY (O&M) | 2022-08-30 17:31 | ### Claro Argentina - NOTICE LA - Torcuato&Cordoba ppusd binary fix and control - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-31 01:13 | Claro AUP - ALL | 1 | Software ¦ Fix
403498 | Claro AR PY UY (O&M) | 2022-08-30 17:27 | CR CTIT 124_2022 - WO0000003888552- CCC_8230- AR - (AR - Triplica con todas las recargas: 05 - 09 - | Minor | Tariff Request | Under investigation |  | Prepaid IN | Fabian Pizzatti | 2022-09-02 16:08 | Claro AUP - ALL
403493 | Claro AR PY UY (O&M) | 2022-08-30 13:47 | ClaroAUP ? PREPAGO - Incident Report - vPPIN PY DS con comportamiento raro. | Minor | Incident Report | Request to Close | External Cause | Prepaid IN | Finocchio Flavio | 2022-08-30 15:06 | Claro AUP - PARAGUAY | 1
403489 | Claro AR PY UY (O&M) | 2022-08-30 12:26 | ClaroAUP - CE - [Incident Report ] ? [ Cancelación de suscripciones en Paraguay ] | Minor | Service Request | Under investigation |  | CE | Correa Aldo David | 2022-08-31 09:00 | Claro AUP - PARAGUAY
403486 | Claro AR PY UY (O&M) | 2022-08-30 11:39 | CTITUY 076_2022 -WO0000003888249- CCC_8239- (Triplica 2 y 5 de septiembre Tn3 UY) [SEVERITY 1] | Minor | Tariff Request | Under investigation |  | Prepaid IN | Fabian Pizzatti | 2022-09-02 16:08 | Claro AUP - URUGUAY
403481 | Claro AR PY UY (O&M) | 2022-08-30 00:17 | Claro AUP - PP - [PLATAFORMA PY Degradación Success Rate ASU-ASR5K-1 | Minor | Incident Report | Request to Close | External Cause | Prepaid IN | Menditto Marco | 2022-08-30 15:07 | Claro AUP - PARAGUAY | 3
403478 | Claro AR PY UY (O&M) | 2022-08-29 17:46 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 30/8/2022 - ON | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-30 01:58 | Claro AUP - ALL | 2.5 | Tariff Activities
403476 | Claro AR PY UY (O&M) | 2022-08-29 17:12 | consulta cdrs tcn3 sin factor multiplicador | Minor | Incident Report | Assigned |  | Prepaid IN | Tarasconi Fernando | 2022-08-29 17:15 | Claro AUP - ALL
403469 | Claro AR PY UY (O&M) | 2022-08-29 10:17 | Caida en indicadores de Renovación de packs | Minor | Incident Report | Assigned |  | Prepaid IN | Garzon Javier | 2022-08-31 10:41 | Claro AUP - ALL
403467 | Claro AR PY UY (O&M) | 2022-08-29 09:54 | TR CTIT 123_2022 - OT: WO0000003884989 - CCC 8243 (Ajuste Oferta Presta Montos y costo de servicio [ | Minor | Tariff Request | Assigned |  | Prepaid IN | Gonzalez Flores German | 2022-08-29 09:55 | Claro AUP - ALL
403460 | Claro AR PY UY (O&M) | 2022-08-28 22:19 | Claro AUP - PP - [PLATAFORMA claro:.Hobbit_Olleros ELEMENTO sdp-1-ssd_010092154065_db_dump] [INC0000 | Minor | Incident Report | Request to Close | Reason Not Applied | Prepaid IN | Dominguez Fuentes Julio | 2022-08-29 00:27 | Claro AUP - ALL | 1
403453 | Claro AR PY UY (O&M) | 2022-08-26 17:02 | CTITPY 059_2022_ALTA_IP_ROAM WO0000003885762 (ALTA DE IP) | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Gillini Federico | 2022-08-30 17:42 | Claro AUP - PARAGUAY | 2
403452 | Claro AR PY UY (O&M) | 2022-08-26 16:59 | CTITUY 075_2022_ALTA_IP_ROAM WO0000003885761 (ALTA DE IP) | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Gillini Federico | 2022-08-30 17:42 | Claro AUP - URUGUAY | 2
403451 | Claro AR PY UY (O&M) | 2022-08-26 16:51 | CR CTIT 122_2022_ALTA_IP_ROAM WO0000003885379 (ALTA DE IP) | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Gillini Federico | 2022-08-30 17:42 | Claro AUP - ALL | 2
403446 | Claro AR PY UY (O&M) | 2022-08-26 10:11 | PMC - ce-db-01/02/03/04 - disk | Minor | Oracle DB O&M | Closed | Data Issue | CE | PMC AR PY UY | 2022-08-26 11:01 | Claro AUP - ALL | 1
403433 | Claro AR PY UY (O&M) | 2022-08-25 15:55 | alta de abonado en tn3 ctp1 | Minor | Incident Report | Request to Close | Data Issue | Prepaid IN | Rodriguez Laura | 2022-08-25 16:35 | Claro AUP - CTP | 1
403426 | Claro AR PY UY (O&M) | 2022-08-25 10:21 | Inconsistencia linea 3884862095 delete_subscriber | Minor | Incident Report | Request to Close | Operation Failure | Prepaid IN | Altamirano Nicolás | 2022-08-26 09:26 | Claro AUP - ALL | 2
403415 | Claro AR PY UY (O&M) | 2022-08-24 12:10 | CR CTIT 121_2022 - WO0000003884915- CCC_8226- AR - (AR - Triplica con todas las recargas: 02 de Sept | Minor | Tariff Request | Assigned |  | Prepaid IN | Fabian Pizzatti | 2022-08-24 12:11 | Claro AUP - ALL
403413 | Claro AR PY UY (O&M) | 2022-08-24 11:36 | CTITUY 074_2022 -WO0000003882899- CCC_8063- (Triplica 30 y 31 de agosto Tn3 UY) [SEVERITY 1] | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-30 17:42 | Claro AUP - URUGUAY | 2
403409 | Claro AR PY UY (O&M) | 2022-08-24 09:52 | INFORMATION REQUEST - PP - MINOR: Error al emitir llamadas - PY | Minor | Information Request | Request to Close | Reason Not Applied | Prepaid IN | Bobrow Lara | 2022-08-29 09:20 | Claro AUP - PARAGUAY | 2
403396 | Claro AR PY UY (O&M) | 2022-08-23 17:12 | Abrir nuevo caso para anlizar problema de emision de llamadas desde prepaga de Paraguay | Minor | Incident Report | Under investigation |  | Prepaid IN | Teruggi Ruben | 2022-08-25 16:36 | Claro AUP - PARAGUAY | 5
403394 | Claro AR PY UY (O&M) | 2022-08-23 14:21 | Claro AUP PP - [Incident report] [Assume positive en Claro Uruguay vPPIN ] INC000030674810 | Minor | Incident Report | Under investigation |  | Prepaid IN | Cavallo Santiago | 2022-09-01 05:54 | Claro AUP - URUGUAY
403391 | Claro AR PY UY (O&M) | 2022-08-23 12:00 | Consulta | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Altamirano Nicolás | 2022-08-23 17:21 | Claro AUP - ALL | 3
403388 | Claro AR PY UY (O&M) | 2022-08-23 11:04 | INFORMATION REQUEST - CR - MINOR: Sin registro de llamadas :AR: | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Priego Balls Diego Mariano | 2022-09-02 12:42 | Claro AUP - ALL | 2
403387 | Claro AR PY UY (O&M) | 2022-08-23 09:49 | ### Claro Argentina - NOTICE LA - PP 4.10.6.4 & 5.6.1.0.1 upgrade - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-24 06:04 | Claro AUP - ALL | 6 | Software ¦ Upgrade
403386 | Claro AR PY UY (O&M) | 2022-08-23 09:41 | TR CTIT 120_2022 - OT: WO0000003882553 - CCC 8216 (Modificación Precio IxD - Prepago - Septiembre) | Minor | Tariff Request | Assigned |  | Prepaid IN | Gonzalez Flores German | 2022-08-23 09:41 | Claro AUP - ALL
403378 | Claro AR PY UY (O&M) | 2022-08-22 17:24 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 23/8/2022 - ON | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-23 02:13 | Claro AUP - ALL | 2 | Tariff Activities
403371 | Claro AR PY UY (O&M) | 2022-08-22 10:36 | Solicitud de Notificaciones - Argentina | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Dominguez Maximiliano | 2022-09-01 18:01 | Claro AUP - ALL | 2
403366 | Claro AR PY UY (O&M) | 2022-08-21 21:34 | Calro AUP - PP- [Incident report] [sdp-1-region8 - db_load_transf] INC000030594979 | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Rojas Angel Guillermo | 2022-08-31 18:00 | Claro AUP - ALL | 1
403356 | Claro AR PY UY (O&M) | 2022-08-19 16:39 | ClaroAUP ? vPPIN - [ Incident Report ] ? [ ccp-1-py - pp_usd ] | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Correa Aldo David | 2022-09-01 11:31 | Claro AUP - PARAGUAY | 2
403337 | Claro AR PY UY (O&M) | 2022-08-19 04:55 | Claro AR PY UY (O&M); ID [397205]; Incident Report PLATAFORMA .Hobbit_Par_Virtual_PP ELEMENTO sdp-1 | Minor | Incident Report | Closed | Operation Failure | Prepaid IN | Menditto Marco | 2022-08-30 18:13 | Claro AUP - PARAGUAY | 1
403336 | Claro AR PY UY (O&M) | 2022-08-19 03:38 | INCIDENT REPORT- PP - MAJOR: InetXDia PY | Major | Incident Report | Closed | Operation Failure | Prepaid IN | Bobrow Lara | 2022-08-30 18:12 | Claro AUP - PARAGUAY | 4
403327 | Claro AR PY UY (O&M) | 2022-08-17 23:23 | DB - ce-mr-06 - disk | Minor | Oracle DB O&M | Closed | No Incident Verified | CE | PMC AR PY UY | 2022-08-31 14:22 | Claro AUP - ALL | 1
403326 | Claro AR PY UY (O&M) | 2022-08-17 22:46 | INCIDENT REPORT- PP - MAJOR: Error al consultar PP_PAYMENT_INTERFACE.Account_Query | Minor | Incident Report | Closed | External Cause | Prepaid IN | Bobrow Lara | 2022-08-30 16:06 | Claro AUP - ALL | 3
403311 | Claro AR PY UY (O&M) | 2022-08-17 14:14 | Claro AUP CE - [Incident report] [CP 2215 con alto porcentaje de bajas] INC000030496046 | Minor | Incident Report | Closed | No Incident Verified | CE | Cavallo Santiago | 2022-09-02 18:31 | Claro AUP - PARAGUAY | 1
403301 | Claro AR PY UY (O&M) | 2022-08-17 11:42 | Claro AUP PP - [Incident report] [Hobbit_Tor_SiteA psp-1_010084056107_DB_cache] INC000030496027 | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Cavallo Santiago | 2022-08-29 13:53 | Claro AUP - SITE A - TORCUATO | 1
403298 | Claro AR PY UY (O&M) | 2022-08-17 11:27 | ### Claro Paraguay - NOTICE LA - PP 5.6.1.0.1 upgrade - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-18 06:32 | Claro AUP - PARAGUAY | 5.5 | Software ¦ Upgrade
403296 | Claro AR PY UY (O&M) | 2022-08-17 10:18 | Solicitud de notificaciones - PRODUCCION PARAGUAY | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Dominguez Maximiliano | 2022-08-29 11:49 | Claro AUP - PARAGUAY | 2
403288 | Claro AR PY UY (O&M) | 2022-08-16 17:25 | Error en la implementación SMS Saldo insuficiente :: TR CTIT 109_2022 - OT: WO0000003867798 - CCC 80 | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Ayne Maria Florencia | 2022-08-31 10:23 | Claro AUP - ALL | 2
403287 | Claro AR PY UY (O&M) | 2022-08-16 16:59 | ### Claro AUP - NOTICE LA - DB Oracle Nodes 03 and 04 restart - UY PY - ON | Minor | Intervention Notification | Closed | Reason Not Applied | CE | LatAm Support AR PY UY | 2022-08-17 01:49 | Claro AUP - ALL | 2 | Hardware ¦ Maintenance
403286 | Claro AR PY UY (O&M) | 2022-08-16 15:05 | Nuevo caso para analizar respuesta 5002 en Diameter - Pruebas CMG | Minor | Incident Report | Under investigation |  | Prepaid IN | Teruggi Ruben | 2022-09-01 17:17 | Claro AUP - ALL | 4
403278 | Claro AR PY UY (O&M) | 2022-08-16 12:57 | Claro AR ? CE - [Service Request] - Problemas con la desactivacion de captcha en CE AR (RV: IP-25847 | Minor | Service Request | Closed | Reason Not Applied | CE | Sander Gustavo | 2022-08-29 15:33 | Claro AUP - ALL | 1
403277 | Claro AR PY UY (O&M) | 2022-08-16 12:52 | CTITUY 073_2022 -WO0000003878256- CCC_8062- (Triplica 24; 26 y 29 de agosto Tn3 UY) [SEVERITY 1] | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-29 09:38 | Claro AUP - URUGUAY | 2
403276 | Claro AR PY UY (O&M) | 2022-08-16 12:28 | CR CTIT 119_2022 - WO0000003877394- CCC_8144- AR - (AR - Triplica con todas las recargas: 26 - 29 de | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-29 09:38 | Claro AUP - ALL | 2
403273 | Claro AR PY UY (O&M) | 2022-08-16 11:41 | Inconsistencia linea 2975344387 | Minor | Incident Report | Closed | Operation Failure | Prepaid IN | Altamirano Nicolás | 2022-08-26 12:40 | Claro AUP - ALL | 1
403272 | Claro AR PY UY (O&M) | 2022-08-16 10:52 | TR CTITPY 058_2022 - OT: WO0000003878249 - CCC 8177 (Tarjetas_Reales_Duplica) [SEVERITY 2] | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Omonte Jose | 2022-08-29 09:38 | Claro AUP - PARAGUAY | 2
403271 | Claro AR PY UY (O&M) | 2022-08-16 10:27 | Claro AUP - PP - [Incident Report] [sdp-1-region8 - db_load_transf - db_dump_remote] INC000030446183 | Minor | Incident Report | Closed | Operation Failure | Prepaid IN | Cavallo Santiago | 2022-08-26 13:55 | Claro AUP - SITE D - ROSARIO | 2
403247 | Claro AR PY UY (O&M) | 2022-08-12 18:59 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 16/8/2022 - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-16 02:13 | Claro AUP - ALL | 3 | Tariff Activities
403243 | Claro AR PY UY (O&M) | 2022-08-12 11:17 | CTITUY 072_2022 - WO0000003876476 - CCC_8150 - (Marcaciones de AWG - UY) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Diaz Agustina | 2022-08-26 11:59 | Claro AUP - URUGUAY | 3
403239 | Claro AR PY UY (O&M) | 2022-08-12 09:56 | PMC - ce-db-01/02/03/04 - disk | Minor | Oracle DB O&M | Closed | Reason Not Applied | CE | PMC AR PY UY | 2022-08-17 14:34 | Claro AUP - ALL | 0.5
403237 | Claro AR PY UY (O&M) | 2022-08-12 07:00 | Claro AUP - PP - [PLATAFORMA claro:.Hobbit_Tor_SiteA ELEMENTO psp-1_010084056107_ASE] [INC0000303359 | Minor | Incident Report | Closed | Software Failure | Prepaid IN | Dominguez Fuentes Julio | 2022-08-12 10:31 | Claro AUP - ALL | 2
403233 | Claro AR PY UY (O&M) | 2022-08-12 03:42 | SERVICE REQUEST - PP - MINOR: DUMPS[ARG] | Minor | Service Request | Assigned |  | Prepaid IN | Priego Balls Diego Mariano | 2022-08-30 17:03 | Claro AUP - ALL
403224 | Claro AR PY UY (O&M) | 2022-08-11 17:07 | Nuevo caso para analizar diferencia en Numero de campos en CDR de SMS Paraguay | Minor | Information Request | Request to Close | Configuration Failure | Prepaid IN | Teruggi Ruben | 2022-08-30 17:02 | Claro AUP - PARAGUAY | 4
403222 | Claro AR PY UY (O&M) | 2022-08-11 14:31 | TR CTIT 118_2022 - OT: WO0000003876767 - CCC 8172 (ALTA PACK 2GBX2D - EXCLUSIVO FACE) [SEVERITY 1] | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 2022-08-29 09:38 | Claro AUP - ALL | 2
403219 | Claro AR PY UY (O&M) | 2022-08-11 11:26 | Claro AUP - PP - [PLATAFORMA .Hobbit_Tor_SiteA ELEMENTO psp-1_010084056107_db_dump_remote] [INC00003 | Minor | Incident Report | Request to Close | Reason Not Applied | Prepaid IN | Dominguez Fuentes Julio | 2022-08-30 17:13 | Claro AUP - ALL | 1
403218 | Claro AR PY UY (O&M) | 2022-08-11 11:05 | Claro AUP - PP - [PLATAFORMA .Hobbit_Tor_SiteA ELEMENTO psp-1_010084056107_ASE] [INC000030307444] | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Dominguez Fuentes Julio | 2022-08-24 09:07 | Claro AUP - ALL | 3
403213 | Claro AR PY UY (O&M) | 2022-08-10 18:45 | Consulta sobre Commerce Engine | Minor | Information Request | Closed | Reason Not Applied | CE | Zelaya Gonzalez Fernando | 2022-08-23 10:42 | Claro AUP - ALL | 1
403212 | Claro AR PY UY (O&M) | 2022-08-10 18:33 | CR CTIT 117_2022 - WO0000003877316- CCC_8142- AR - (AR - Triplica con todas las recargas: 16 19 - 2 | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-26 11:59 | Claro AUP - ALL | 3
403209 | Claro AR PY UY (O&M) | 2022-08-10 16:42 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 11/8/2022 - ON | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-11 03:13 | Claro AUP - ALL | 4 | Tariff Activities
403208 | Claro AR PY UY (O&M) | 2022-08-10 15:58 | Consulta numeros | Minor | Incident Report | Closed | Reason Not Applied | Prepaid IN | Altamirano Nicolás | 2022-08-24 09:06 | Claro AUP - ALL | 2
403207 | Claro AR PY UY (O&M) | 2022-08-10 14:56 | SERVICE REQUEST - PP - MINOR: problemas para crear linea en maqueta | Minor | Service Request | Request to Close | Data Issue | Prepaid IN | Diaz Gonzalo Javier | 2022-08-30 17:08 | Claro AUP - CTP | 1
403204 | Claro AR PY UY (O&M) | 2022-08-10 14:15 | ### Claro Argentina - NOTICE LA - PP 4.10.6.4 & 5.6.1.0.1 upgrade - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-11 05:56 | Claro AUP - ALL | 6 | Software ¦ Upgrade
403199 | Claro AR PY UY (O&M) | 2022-08-10 11:05 | CTITUY 071_2022 -WO0000003876731- CCC_8061- (Triplica 17; 19 y 22 de agosto Tn3 UY) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-26 11:59 | Claro AUP - URUGUAY | 3
403198 | Claro AR PY UY (O&M) | 2022-08-10 10:15 | TR CTITPY 056_2022 - OT: WO0000003876413 - CCC 8167 (Promocion_Plus_Baja_Cuadruplica_Alta_Duplica) | Minor | Tariff Request | Request to Close | Reason Not Applied | Prepaid IN | Omonte Jose | 2022-08-29 09:42 | Claro AUP - PARAGUAY | 2
403197 | Claro AR PY UY (O&M) | 2022-08-10 10:15 | Solicitud de notificaciones - PRODUCCION ARGENTINA | Minor | Information Request | Closed | No identified Cause | Prepaid IN | Dominguez Maximiliano | 2022-08-22 12:39 | Claro AUP - ALL | 2
403194 | Claro AR PY UY (O&M) | 2022-08-10 09:00 | INFORMATION REQUEST - CE - MINOR: Error en suscripción Claro Parking - UY | Minor | Information Request | Closed | Reason Not Applied | CE | Bobrow Lara | 2022-08-22 12:39 | Claro AUP - URUGUAY | 1
403192 | Claro AR PY UY (O&M) | 2022-08-09 20:40 | Claro AUP - PP - [Incident Report] [sdp-1-region8 - db_load_transf] | Minor | Incident Report | Closed | Configuration Failure | Prepaid IN | Rojas Angel Guillermo | 2022-08-22 15:46 | Claro AUP - ALL | 4
403186 | Claro AR PY UY (O&M) | 2022-08-09 18:06 | CTITUY 070_2022 - WO0000003876704 - CCC_8117 - (BAJA 71112 - Inetworks SRL - UY) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Diaz Agustina | 2022-08-26 11:59 | Claro AUP - URUGUAY | 3
403181 | Claro AR PY UY (O&M) | 2022-08-09 15:32 | PMC - ce-db-03/04 queue_PY | Minor | Oracle DB O&M | Closed | Software Failure | CE | PMC AR PY UY | 2022-08-22 13:30 | Claro AUP - ALL | 1
403169 | Claro AR PY UY (O&M) | 2022-08-08 18:47 | ### Claro AUP - NOTICE LA - Support - Tariff Execution of TR sentences - 9/8/2022 - ON | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 2022-08-09 02:13 | Claro AUP - ALL | 2 | Tariff Activities
403165 | Claro AR PY UY (O&M) | 2022-08-08 16:39 | PMC - ce-db-03/04 - queue_PY | Minor | Oracle DB O&M | Closed | Reason Not Applied | CE | PMC AR PY UY | 2022-08-19 10:35 | Claro AUP - PARAGUAY | 1
403161 | Claro AR PY UY (O&M) | 2022-08-08 15:08 | Consulta respecto a saldos al suspenderse y cancelarse líneas en AUP | Minor | Information Request | Request to Close | Reason Not Applied | Prepaid IN | Perez Gabriela Belen | 2022-08-30 17:06 | Claro AUP - ALL | 6
403159 | Claro AR PY UY (O&M) | 2022-08-08 14:14 | Claro AUP - PP - [PLATAFORMA .Hobbit_Par_Virtual_PP ELEMENTO cgw-5-py_010101007035_memory] [INC00003 | Minor | Incident Report | Closed | Software Failure | Prepaid IN | Dominguez Fuentes Julio | 2022-08-22 15:46 | Claro AUP - PARAGUAY | 1
403157 | Claro AR PY UY (O&M) | 2022-08-08 13:06 | CTITPY 055_2022 - WO0000003872800 - CCC_8165 - (PACKS POSTVENTA - Cambio de Precio) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 2022-08-26 11:59 | Claro AUP - PARAGUAY | 3
403153 | Claro AR PY UY (O&M) | 2022-08-08 09:50 | Claro AUP - PP - [Incident Report] [ Revisión de Parámetros de Seguridad (C21) ] | Minor | Service Request | Under investigation | Reason Not Applied | Prepaid IN | Correa Aldo David | 2022-08-10 11:16 | Claro AUP - ALL
403148 | Claro AR PY UY (O&M) | 2022-08-08 08:03 | Claro AUP - PP - [PLATAFORMA claro:.Hobbit_Tor_SiteA ELEMENTO cgw-10-region1_010084056123_memory] [I | Minor | Incident Report | Closed | Capacity Overloaded | Prepaid IN | Dominguez Fuentes Julio | 2022-08-19 10:25 | Claro AUP - SITE A - TORCUATO | 2
403131 | Claro AR PY UY (O&M) | 2022-08-05 17:56 | TR CTIT 115_2022 - OT: WO0000003873736 - CCC 8149 (Inc. SMS Internacional - Masivo CR y CO) [SEVER | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 2022-08-26 11:59 | Claro AUP - ALL | 3
403125 | Claro AR PY UY (O&M) | 2022-08-05 09:37 | Linea para borrar | Minor | Incident Report | Closed | Operation Failure | Prepaid IN | Altamirano Nicolás | 2022-08-17 09:57 | Claro AUP - ALL | 1
403124 | Claro AR PY UY (O&M) | 2022-08-05 06:01 | Claro AUP - PP - [Incident report] [PLATAFORMA .Hobbit_Ros_SiteD ELEMENTO sdp-1-region8_010076025187 | Minor | Incident Report | Under investigation |  | Prepaid IN | Menditto Marco | 2022-08-05 15:59 | Claro AUP - SITE D - ROSARIO
403118 | Claro AR PY UY (O&M) | 2022-08-04 18:04 | lineas en CE de labo | Minor | Service Request | Closed | Reason Not Applied | CE | Rodriguez Laura | 2022-08-19 10:25 | Claro AUP - ALL | 1
403106 | Claro AR PY UY (O&M) | 2022-08-04 06:45 | SERVICE REQUEST - PP - MINOR: DUMPS[ARG] | Minor | Service Request | Closed | Reason Not Applied | Prepaid IN | Sanchez Eduardo | 2022-08-17 09:47 | Claro AUP - ALL | 2
403102 | Claro AR PY UY (O&M) | 2022-08-03 18:18 | CR CTIT 116_2022 - WO0000003870799- CCC_8140 - AR - (AR - Triplica con todas las recargas: 12 de Ago | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 2022-08-26 11:59 | Claro AUP - ALL | 3
403101 | Claro AR PY UY (O&M) | 2022-08-03 16:39 | TR CTIT 113_2022 - OT: WO0000003870790 - CCC 8123 (Planes 25GB : Incluir Qatar como beneficio CR) [ | Minor | Tariff Request | Assigned |  | Prepaid IN | Omonte Jose | 2022-09-02 10:42 | Claro AUP - ALL
403100 | Claro AR PY UY (O&M) | 2022-08-03 15:56 | Consulta sobre horarios de SMS | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Bobrow Lara | 44788.6889 | Claro AUP - ALL | 1
403098 | Claro AR PY UY (O&M) | 2022-08-03 14:31 | INFORMATION REQUEST - PP - MINOR: inconveniente tarifación roaming datos UY - profile 454 | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Bobrow Lara | 44790.6639 | Claro AUP - URUGUAY | 3
403097 | Claro AR PY UY (O&M) | 2022-08-03 14:21 | CTITUY 069_2022 -WO0000003870782- CCC_8060- (Triplica 10; 11; 12 y 15 de agosto Tn3 UY) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 44799.4993 | Claro AUP - URUGUAY | 2
403096 | Claro AR PY UY (O&M) | 2022-08-03 13:39 | CTITUY 068_2022- OT: WO0000003871923- CCC 8086 (Alta Bulk BRADITEX SA) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 44799.4993 | Claro AUP - URUGUAY | 2
403095 | Claro AR PY UY (O&M) | 2022-08-03 13:00 | CR CTIT 114_2022 - OT: WO0000003870775- CCC 8107 (ALTA MARCACIONES - ALCASAGAR / NUEVO INTEGRADOR SM | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 44799.4993 | Claro AUP - ALL | 2
403093 | Claro AR PY UY (O&M) | 2022-08-03 11:39 | CR CTIT 112_2022 - OT: WO0000003870769- CCC 8108 (SMS BULK A2P - Integrador MOVILGATE - Marcación 22 | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Fabian Pizzatti | 44799.4993 | Claro AUP - ALL | 2
403092 | Claro AR PY UY (O&M) | 2022-08-03 11:07 | CTITPY 054_2022 - WO0000003870767 - CCC_8130 - (Pack noches - Modificación) [SEVERITY 1] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 44799.4993 | Claro AUP - PARAGUAY | 2
403089 | Claro AR PY UY (O&M) | 2022-08-03 09:10 | ### Claro Argentina - NOTICE LA - PP 5.6.1.0.1 upgrade - ON ### | Minor | Intervention Notification | Closed | Reason Not Applied | Prepaid IN | LatAm Support AR PY UY | 44777.2681 | Claro AUP - ALL | 6 | Software ¦ Upgrade
403088 | Claro AR PY UY (O&M) | 2022-08-03 09:02 | Release 5.6.1: Solicitud de notificaciones - PRODUCCION ARGENTINA | Minor | Information Request | Closed | Reason Not Applied | Prepaid IN | Dominguez Maximiliano | 44788.4076 | Claro AUP - ALL | 1
403086 | Claro AR PY UY (O&M) | 2022-08-02 22:13 | ce-db-03 - queue_PY | Minor | Oracle DB O&M | Closed | Software Failure | CE | PMC AR PY UY | 44788.4347 | Claro AUP - PARAGUAY | 1
403085 | Claro AR PY UY (O&M) | 2022-08-02 21:38 | ClaroAUP ? Commerce Engine - [ Incident Report ] ? [ CP Mobilespace; Tariff 14172 - Package 9446; HE | Minor | Incident Report | Closed | External Cause | CE | Canepa Guillermo | 44788.4347 | Claro AUP - PARAGUAY | 1
403078 | Claro AR PY UY (O&M) | 2022-08-02 12:00 | ClaroAUP ? CE AR - Service Request[MAYOR] - Consulta por aumento de cobros escalonados (TD_REQUESTED | Minor | Information Request | Closed | Reason Not Applied | CE | Farias Cristian G. | 44785.6104 | Claro AUP - ALL | 1
403074 | Claro AR PY UY (O&M) | 2022-08-02 10:15 | TR CTIT 111_2022 - OT: WO0000003870739 - CCC 8112 (Cambio de Precio SMS Internacional) [SEVERITY 2] | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 44799.4993 | Claro AUP - ALL | 3
403065 | Claro AR PY UY (O&M) | 2022-08-01 17:49 | TR CTIT 110_2022 - OT: WO0000003869371 - CCC 8084 (Baja de beneficio en Recargas desde $400 (Masivo | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 44799.4993 | Claro AUP - ALL | 2
403062 | Claro AR PY UY (O&M) | 2022-08-01 14:13 | PMC - ccp-1-py - notiff_smpp | Minor | Incident Report | Closed | No Incident Verified | Prepaid IN | PMC AR PY UY | 44776.7139 | Claro AUP - PARAGUAY | 1
403058 | Claro AR PY UY (O&M) | 2022-08-01 11:51 | Encolamiento de notificaciones PY | Minor | Information Request | Closed | Reason Not Applied | CE | Nuñez Matias Nicolas | 44791.5111 | Claro AUP - PARAGUAY | 1
403055 | Claro AR PY UY (O&M) | 2022-08-01 10:48 | TR CTIT 109_2022 - OT: WO0000003867798 - CCC 8083 (SMS saldo insuficiente - Cambio PP Mensual Recar | Minor | Tariff Request | Closed | Reason Not Applied | Prepaid IN | Gonzalez Flores German | 44799.4993 | Claro AUP - ALL | 3

## Consolidated
Type | June | July | August
Incident Report | 21 | 17 | 31
Tariff Request | 32 | 31 | 31
Service Request | 6 | 7 | 7
Oracle DB O&M | 9 | 9 | 6
Information Request | 12 | 12 | 15
Intervention Notification | 7 | 9 | 12
Total | 85 | 102 | 102
Current Month
31
31
7
6
15
12
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Type
Type | #
Tariff Request | 31
Incident Report | 31
Information Request | 15
Intervention Notification | 12
Service Request | 7
Oracle DB O&M | 6
Total | 102
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Severity
Severity | #
Minor | 101
Major | 1
TYPE | Incident Report
Severity | #
Minor | 30
Major | 1
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Reason
Reason | #
Reason Not Applied | 63
Blanks | 15
Operation Failure | 6
External Cause | 4
Software Failure | 4
Data Issue | 3
No Incident Verified | 3
Configuration Failure | 2
No identified Cause | 1
Capacity Overloaded | 1
Total | 102
TYPE | Incident Report
Reason | #
Reason Not Applied | 8
Blanks | 6
Operation Failure | 6
External Cause | 4
Software Failure | 2
No Incident Verified | 2
Configuration Failure | 1
Data Issue | 1
Capacity Overloaded | 1
Total | 31
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Status
Status | #
Closed | 67
Request to Close | 19
Under investigation | 9
Assigned | 7
Total | 102
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Product
TYPE | (Todas)
Product | #
Prepaid IN | 86
CE | 16
Total | 102
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Information
Information Request
Month | Hours
January | 13
February | 15
March | 23
April | 36.5
May | 19
June | 28
July | 24
August | 31
September
October
November
December
Total 2022 | 189.5
Hours - Current Report |  | 31
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Interventions
TYPE | Intervention Notification
Activity Type | #
Tariff Activities | 6
Software ¦ Upgrade | 4
Software ¦ Fix | 1
Hardware ¦ Maintenance | 1
Total | 12
Intervention Notification
Month | Hours
January | 26
February | 19.5
March | 33.5
April | 23
May | 34.3
June | 12
July | 25.2
August | 41
September
October
November
December
Total 2022 | 214.5
Hours - Current Report | 41
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT

## Tables
CASEID | DATETIME | FOUND BY | PRODUCT | SUBJECT
403409 | 2022-08-24 09:52 | Bobrow Lara | Prepaid IN | INFORMATION REQUEST - PP - MINOR: Error al emitir llamadas - PY
403388 | 2022-08-23 11:04 | Priego Balls Diego Mariano | Prepaid IN | INFORMATION REQUEST - CR - MINOR: Sin registro de llamadas :AR:
403371 | 2022-08-22 10:36 | Dominguez Maximiliano | Prepaid IN | Solicitud de Notificaciones - Argentina
403356 | 2022-08-19 16:39 | Correa Aldo David | Prepaid IN | ClaroAUP ? vPPIN - [ Incident Report ] ? [ ccp-1-py - pp_usd ]
403296 | 2022-08-17 10:18 | Dominguez Maximiliano | Prepaid IN | Solicitud de notificaciones - PRODUCCION PARAGUAY
403224 | 2022-08-11 17:07 | Teruggi Ruben | Prepaid IN | Nuevo caso para analizar diferencia en Numero de campos en CDR de SMS Paraguay
403213 | 2022-08-10 18:45 | Zelaya Gonzalez Fernando | CE | Consulta sobre Commerce Engine
403197 | 2022-08-10 10:15 | Dominguez Maximiliano | Prepaid IN | Solicitud de notificaciones - PRODUCCION ARGENTINA
403194 | 2022-08-10 09:00 | Bobrow Lara | CE | INFORMATION REQUEST - CE - MINOR: Error en suscripción Claro Parking - UY
403161 | 2022-08-08 15:08 | Perez Gabriela Belen | Prepaid IN | Consulta respecto a saldos al suspenderse y cancelarse líneas en AUP
403100 | 2022-08-03 15:56 | Bobrow Lara | Prepaid IN | Consulta sobre horarios de SMS
403098 | 2022-08-03 14:31 | Bobrow Lara | Prepaid IN | INFORMATION REQUEST - PP - MINOR: inconveniente tarifación roaming datos UY - profile 454
403088 | 2022-08-03 09:02 | Dominguez Maximiliano | Prepaid IN | Release 5.6.1: Solicitud de notificaciones - PRODUCCION ARGENTINA
403078 | 2022-08-02 12:00 | Farias Cristian G. | CE | ClaroAUP ? CE AR - Service Request[MAYOR] - Consulta por aumento de cobros escalonados (TD_REQUESTED
403058 | 2022-08-01 11:51 | Nuñez Matias Nicolas | CE | Encolamiento de notificaciones PY
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.

## SLA Cases
Case id | Customer | Subject | Severity | Status | Products | Opened | Closed | Recovery Time | Solution Time | RT Exceeded | FS Exceeded | RT Status | FS Status
403336 | Claro AR PY UY (O&M) | INCIDENT REPORT- PP - MAJOR: InetXDia PY | Major | Closed | Prepaid IN | 2022-08-19 03:38 | 2022-08-19 07:56 | 4:18 | 4:18 | 0:00 | 0:00 | OK | OK

## SLA
SLA OVERVIEW
Rule | Time limit | Count of cases | # of cases exceeding | Rule | Time limit | Count of cases | # of cases exceeding
SLA Recovery Time Critical | 0.083333 | 0 | 0 | SLA Recovery Time Major | 1 | 1 | 0
SLA Final Solution Critical | 1 | 0 | 0 | SLA Final Solution Major | 3 | 1 | 0
SLA Recovery Time Major | 1 | 1 | 0 | SLA Recovery Time Major | 1 | 1 | 0
SLA Final Solution Major | 3 | 1 | 0 | SLA Final Solution Major | 3 | 1 | 0
SLA - RECOVERY TIME - CRITICAL
OK | 0
NOK | 0
SLA - FINAL SOLUTION - CRITICAL
OK | 0
NOK | 0
SLA - RECOVERY TIME - MAJOR
OK | 1
NOK | 0
SLA - FINAL SOLUTION - MAJOR
OK | 1
NOK | 0
TECNOTREE CUTOMER SUPPORT - MONTHLY REPORT